## Feuil1
SCG007 CHASSIS #01 JOB LIST Post 21T01 Vall/For 21T02Monz
| Chassis mileage | 319
| Mileage done in last event | 319
| Mileage expected for next event | 1500
| TASKS | PRIORITY | DEADLINE | DONE | NOTES
CHASSIS | SETDOWN end FP4 | 1 | 2021-03-01 | 2017-10-10
| Prepare possible ballasts for WD sweep | 2 | 2021-03-02
| Wiper to fit (protect windscreen with heli tape) | 1 | 2021-03-03
SPLITTER | Check and repair if necessary | 1 | 2021-03-02
REAR BLOCK | Check and repair if necessary | 1 | 2021-03-02
BODYWORK | Reinforce rear brakes ducts sticking on engine cover | 1 | 2021-03-02
| Rear right clip with engine cover and rear block to fit | 1 | 2021-03-02
| Floor to be repaired | 1 | 2021-03-02
| Plank measurement | 1 | 2021-03-02
| Rear end connector connection to be adjusted | 1 | 2021-03-02
FRONT SUSPENSION | Check tightening and free play | 1 | 2021-03-02
| Dampers visual check | 1 | 2021-03-02
| Prepare packers of 2 /5 /10mm for dampers | 1 | 2021-03-03
| Prepare shims of 2 / 5 mm for Pushrods | 1 | 2021-03-03
REAR SUSPENSION | Check tightening and free play | 1 | 2021-03-02
| Understand why static RRH is going down in FP3 (rear suspension settlement?) | 1 | 2021-03-02
| Dampers visual check | 1 | 2021-03-02
| Prepare packers of 2 /5 /10mm for dampers | 1 | 2021-03-03
| Prepare shims of 2 / 5 mm for Pushrods | 1 | 2021-03-03
STEERING RACK | Steering wheel move from side to side to fix | 1 | 2021-03-03
| Prepare spacers to have steering wheel lower | 2 | 2021-03-03
BRAKES | Brakes wear measurements | 1 | 2021-03-01
| Brakes ducts check and repair | 1 | 2021-03-02
| Brakes scoops check and repair | 1 | 2021-03-02
GB - BELLHOUSING | Check gear ratios | 1 | 2021-03-02
| Check differential preload at wheel | 1 | 2021-03-02
| Fit a residual pressure valve (Sobek?) | 1 | 2021-03-02
| Check GB oil | 1 | 2021-03-02
COCKPIT/ PEDAL BOX | Check driver height postion vs headrest/siderest | 2 | 2021-03-03
| System to make drivers able to close the doors when are in car. | 2 | 2021-03-03
| Reinforce cover under windscreen sticking | 1 | 2021-03-03
| BB adjuster sticker to fit in the right directions information | 1 | 2021-03-03
| Prepare soft throttle spring | 2 | 2021-03-03
| Cockpit lights/Steering wheel-Switch panel ilumination/Driver helper light system | 3
COOLING SYSTEM | Visual check of radiators | 1 | 2021-03-02
| Check water and oil levels | 1 | 2021-03-02
FUEL TANK | Venting side to improve | 2 | 2021-03-03
| Prepressurize system after drain out to fit | 2 | 2021-03-03
ELECTRONICS | TPMS to make working | 1 | 2021-03-03
| Rear left laser sensors did not work correctly - To fix | 1 | 2021-03-03
| Back-up radio to make working | 1 | 2021-03-03
| Steering wheel buttons to move (FCY and drink swap,..) | 1 | 2021-03-03
| Visible labels on steering wheel | 1 | 2021-03-03
| TC mapping to prepare | 1 | 2021-03-03
| More PWR steering assistance to prepare | 2 | 2021-03-03
| Alarm for restart if not in 1st gear | 1 | 2021-03-03
| Brake balance info to fit in a dashboard page | 1 | 2021-03-03
| Laptime on dashboard to fit | 1 | 2021-03-03
| Settings change information on dahboard | 1 | 2021-03-03
| Prepare launch control | 1 | 2021-03-03
ENGINE | Do a fire-Up procedure ( already asked to Damien from Pipo moteurs) | 1 | 2021-03-03
| Set engine alarms | 1 | 2021-03-03
| Remove oil and check it | 1 | 2021-03-02
EQUIPMENT | Car identifcation and pit recognition light system | 2 | 2021-03-03
| Rims mileage | 1 | 2021-03-01